## Tender Summary (SOT)
HOLY BUILDERS SDN. BHD.
BDA/CT/52/2026 - THE PROPOSED PROVISION AND LAYING OF WATERPROOFING MEMBRANE TO EXISTING ROOF BALCONIES AND ASSOCIATED WORKS AT WISMA BINTULU BUILDING (REMAINING WORKS)
SUMMARY OF TENDER - PRICED ¦ Tender date: 12 October 2026 ¦ Validity: 90 days ¦ Warranty: 2 years on waterproofing works
Item | Description | Qty | Unit | Rate (RM) | Amount (RM)
1.0 | Preliminaries and Generally - specifications, conditions of contract, working hours, service elevator restrictions, safety & working at height, site cleanliness |  | LUMP SUM |  | 471539.2
2.0 | New Rain Water Down Pipe / Floor Trap
2.1 | Coring work (110 mm dia.) to slab - identifying coring points, tests and PE-endorsed report |  | LUMP SUM |  | 20005.28
2.2 | Coring 110 mm dia. to floor slab / RC gutter wall for new floor traps / RWDP (1st floor gutter wall, 3rd, 4th, 5th, 6th floor slabs) |  | LUMP SUM |  | 32260.14
2.3 | Decommissioning of existing RWDP - dewatering, 4" PVC end caps, concrete to existing floor trap openings |  | LUMP SUM |  | 9004.42
2.4 | Supply and install new 110 mm dia. uPVC (SIRIM) RWDP / floor trap, 3.2 mm thk c/w tees, elbows, connections, clips, access through glazing (outlet to existing RC gutter at Level 1) |  | LUMP SUM |  | 117104.37
3.0 | Demolition and associated works - removing, carting away debris and making good |  | LUMP SUM |  | 7526.4
3.1 | Hacking work to existing cement screed and waterproofing (remaining portion) |  | LUMP SUM |  | 119279.88
4.0 | Screeding & Waterproofing System
4.1 | Prepare surface, patching / repair of cracks, rectify ponding, thorough cleaning of RC slab |  | LUMP SUM |  | 59158.48
4.2 | Supply and apply 3 layer coat of SikaTop Seal-107 (MY) on entire RC slab - 3rd, 4th, 5th, 6th floor |  | LUMP SUM |  | 164184.78
4.3 | Cement and sand screeding to falls incl. forming new scupper drain, steel trowel finish, movement joints, BRC 610 mesh - 3rd, 4th, 5th, 6th floor |  | LUMP SUM |  | 244254.12
4.4 | Supply and apply 3 layers Sikalastic-632 R on new screed and scupper drain - 3rd, 4th, 5th, 6th floor |  | LUMP SUM |  | 527230.89
4.5 | Up-turns along wall and glass work along concrete balcony incl. raking columns, fittings & finishes to match existing - 3rd, 4th, 5th, 6th floor |  | LUMP SUM |  | 80409.22
5.0 | RC Gutter - high-pressure cleaning, removal of unwanted material, repair of cracks / honeycomb, 3 layers Sikalastic-632 R to gutter floor and wall |  | LUMP SUM |  | 191246.73
6.0 | Silicone seal - make good existing silicone along wall and glass at all balconies |  | LUMP SUM |  | 16929.76
7.0 | Provisional Items
7.1 | Removal of existing defective ceiling incl. temporary dismantling of light fittings | 2500 | M2 | 7.81 | 19525
7.2 | New prime flex 3 mm ceiling incl. reinstating light fittings, plastering joints | 2500 | M2 | 41.41 | 103525
7.3 | Repair work to existing ceiling wooden structure | 0.3 | M3 | 6292.48 | 1887.744
7.4 | Painting to repaired internal ceiling - alkali-resisting primer + 2 coats Dulux Pentalite | 2500 | M2 | 12.88 | 32200
7.5 | Replace rusty / broken aluminium flashing with new 1.0 mm aluminium flashing c/w caulking | 20 | M2 | 204.29 | 4085.8
7.6 | Grouting to repair cracks on existing slab | 300 | Point | 65.28 | 19584
A | SUB-TOTAL ITEMS 1.0 - 7.6 |  |  |  | 2240941.214
B | Insurance (CAR, workmen) & performance bond charges (% of A) |  |  | 1.2% | 34420.86
8. | Provisional Sum for Sales and Service Tax (SST) |  |  |  | 80000
| TOTAL TO BE CARRIED TO FORM OF TENDER (RM) |  |  |  | 2355362
PRICE ANALYSIS (for internal use - remove before submission)
| Net cost of works (materials + labour + plant), items 1.0-6.0 |  |  |  | 1580275.5225
| of which: Materials |  |  |  | 871659.9143
| of which: Labour (manpower) |  |  |  | 323686.4815
| of which: Plant, logistics & preliminaries |  |  |  | 384929.1267
| Warranty provision (2 years) |  |  |  | 29203.8981
| Margin @ 28% (items 1.0-6.0) |  |  |  | 450654.2378
| Tender price items 1.0-6.0 |  |  |  | 2060133.67
| Provisional items 7.1-7.6 (at tender rates) |  |  |  | 180807.544
| Tender total per m² of balcony + gutter area treated (RM/m²) |  |  |  | 605.826
Notes to tenderer (internal):
- All lump sums are built up on the "Rate Build-up" and "Item Pricing" sheets and can be produced as the detailed breakdown the S.O. may request.
- Method statement, Sika brochures / PDS and the 2-year warranty undertaking to be submitted with the tender (Mandatory Requirement, item 53 of P&G).
- Working hours per S.O. approved schedule; no use of service elevator for waste - all debris lowered by crane / chute (priced in 1.0 and 3.1).
- Quantities measured from the contract drawings; the tenderer is deemed to have obtained own quantities - site verification recommended before submission.
SIGN AND STAMP : ____________________________ DATE : ______________

## Rates & Inputs
HOLY BUILDERS SDN. BHD.
RATES & INPUTS - BDA/CT/52/2026 WATERPROOFING, WISMA BINTULU (REMAINING WORKS)
All yellow cells are inputs. Material prices are indicative Malaysian 2025/26 figures - replace with supplier quotations (Sika Kimia Sdn Bhd, local hardware) before submission.
1. COMMERCIAL SETTINGS
Margin on net cost (overheads & profit) | 28% | % | As instructed: 28%
Warranty provision - 2 years defects / waterproofing warranty | 3% | % of net cost of waterproofing items | Allowance for call-backs, re-coating, Sika extended warranty admin over 2 years; applied to items 4.2-4.5, 5.0, 6.0
Provisional Sum for SST (fixed by BQ item 8) | 80000 | RM | Carried as stated in the BQ
Contract programme | 16 | weeks | Assumed duration for preliminaries, supervision and plant hire
Working days per week | 6 | days
Material wastage allowance | 18% | % | 18% top-up on all materials (as instructed)
2. MATERIAL PRICES (delivered to site, excl. SST)
SikaTop Seal-107 (MY) 25 kg set | 165 | RM/set | Sika Kimia / stockist quote required
Sikalastic-632 R 21 kg pail | 980 | RM/pail
Sikalastic U-Primer 14 kg pail | 520 | RM/pail
Sika Reemat Premium 50 m² roll | 480 | RM/roll
Sikaflex-11 FC+ 300 ml cartridge | 26 | RM/no.
SikaTop-122 / MonoTop repair mortar 25 kg | 125 | RM/bag
Sika Thinner C 5 L | 65 | RM/tin
Portland cement 50 kg bag | 23 | RM/bag
Washed sand (screed) | 75 | RM/m³ | Delivered Bintulu
BRC A6 / 610 mesh 2.4 x 4.8 m sheet | 95 | RM/sheet | 11.52 m² per sheet
Movement joint - bitumen board 10 mm + PU sealant | 28 | RM/m
uPVC 110 mm Class D pipe 5.8 m (SIRIM) | 68 | RM/length
uPVC 110 mm fittings (tee / elbow / coupling) average | 28 | RM/no.
uPVC 110 mm pipe clip / bracket c/w anchor | 12 | RM/no.
Floor trap 110 mm c/w stainless grating cover | 85 | RM/no.
4" PVC end cap | 9 | RM/no.
Concrete / grout for sealing existing trap opening (per opening) | 18 | RM/no.
Silicone sealant (neutral cure, as existing) 300 ml | 22 | RM/no. | ~8 m per cartridge
Aluminium flashing 1.0 mm sheet, fabricated | 95 | RM/m²
Crack injection grout / epoxy per point | 32 | RM/point
Prime flex 3 mm ceiling board (supply) | 14 | RM/m²
Timber (treated) for ceiling structure | 3200 | RM/m³
Dulux alkali-resisting primer + 2 coats Pentalite (material) | 4.5 | RM/m²
Water & misc. consumables | 0.5 | RM/m²
3. LABOUR RATES (all-in, incl. EPF/SOCSO, levy, accommodation, transport)
Site supervisor / foreman | 280 | RM/day
Skilled waterproofing applicator (Sika-trained) | 190 | RM/day
Screeder / mason | 180 | RM/day
Plumber / coring operator | 190 | RM/day
General worker | 115 | RM/day
Site safety supervisor | 260 | RM/day
Professional Engineer - coring assessment & endorsed report | 9000 | RM lump sum | Item 2.1
Rebar scanning (GPR / cover meter) per point | 15 | RM/point | Item 2.1
4. PLANT, LOGISTICS & PRELIMINARIES RATES
Mobile crane 100 t all-terrain, daily hire incl. operator | 5800 | RM/day | From crane & logistics workbook
Crane mobilisation / demobilisation per call-out | 8000 | RM/no.
Rigger / signalman | 150 | RM/day
Crane lifts per day (0.85 t payload) | 49 | lifts/day | 7 lifts/h x 7 h
Number of crane call-outs | 6 | no. | Per floor + gutter
Debris chute / skip hire per floor set-up | 1200 | RM/floor
Waste skip / lorry disposal to contractor dumping ground | 480 | RM/trip | ~5 t per trip
Material delivery lorry (10 t) per trip | 650 | RM/trip
Coring machine hire + diamond bit wear per point | 22 | RM/point
High-pressure water jet (150 bar) hire | 180 | RM/day
Mixer, grinder, vacuum, small tools | 900 | RM/week
Edge protection / mobile scaffold hire | 2200 | RM/week | Perimeter guard rails + tower for raking columns
Site office, store container, toilet, water & electricity | 2400 | RM/week
Insurance (CAR, workmen) & performance bond charges | 1.2% | % of tender | Applied to contract sum before SST
HSE: PPE, harnesses, signage, barricades, lifting plan | 9500 | RM lump
Site mobilisation / demobilisation, hoarding, cleaning | 12000 | RM lump
Method statement, shop drawings, as-built, testing (flood tests), Sika warranty | 6500 | RM lump
5. PRODUCTIVITY / OUTPUTS (per man-day)
Hacking existing screed & waterproofing incl. loading debris | 7 | m²/man-day
Surface preparation, patching, cleaning (item 4.1) | 35 | m²/man-day
SikaTop Seal-107, 3 coats (incl. mixing) | 38 | m²/man-day | Per coat ~115 m²
Cement-sand screed to falls c/w BRC, steel trowel | 11 | m²/man-day
Sikalastic U-Primer + 3 layers Sikalastic-632 R | 32 | m²/man-day
Up-turns 300 mm (107 + 632 R + Reemat) | 9 | m²/man-day
RC gutter cleaning (water jet) & repair | 22 | m²/man-day
RC gutter 3 layers Sikalastic-632 R floor & wall | 28 | m²/man-day
Coring 110 mm incl. setting out & making good | 7 | points/man-day | 2-man crew = 14 points/day
uPVC 110 mm RWDP install on raking column | 14 | m/man-day | Incl. clips, fittings, access
Silicone removal & re-sealing | 35 | m/man-day
Ceiling removal (item 7.1) | 25 | m²/man-day
Prime flex ceiling install (item 7.2) | 12 | m²/man-day
Ceiling painting primer + 2 coats (item 7.4) | 40 | m²/man-day
Aluminium flashing replacement | 4 | m²/man-day
Crack grouting | 10 | points/man-day

## Quantities
HOLY BUILDERS SDN. BHD.
QUANTITY TAKE-OFF (from CAD file Waterproofing_Contract.dwg and drawings BDA-MWS/BLD/1/2025)
Plan areas measured from the drawing hatches; counts from drawing symbols. Yellow = inputs / assumptions to verify on site.
1. AREAS (m²)
Floor | Balcony slab incl. scupper drain (m²) | of which scupper drain (m²) | RC gutter plan area (m²) | Remarks
3rd Floor | 1068.32 | 110.49 | 0 | Green floor hatch + yellow drain hatch, overlap removed
4th Floor | 889.81 | 96.79 | 0
5th Floor | 619.6 | 72.02 | 0
6th Floor | 380.76 | 58.6 | 0 | Drain ring lies inside the floor ring
1st Floor | 0 | 0 | 309.84 | Gutter 99.6 m OD x 1.0 m wide, 1.0 m deep (assumed)
TOTAL | 2958.49 | 337.9 | 309.84
2. DERIVED QUANTITIES
RC gutter depth (wall height) | 1 | m | Assumed - not shown on drawing; verify on site
RC gutter centre-line length | 309.761 | m | Mean circumference
RC gutter wall area (both sides) | 619.5221 | m²
RC gutter total coated area (floor + walls) | 929.3621 | m² | Item 5.0 Sikalastic-632 R
Existing screed & waterproofing to hack (item 3.1) | 2958.49 | m² | Whole balcony slab 3rd-6th; BQ notes part already done - see % below
Portion of hacking already completed by previous contractor | 0% | % | Set from site inspection; 0% = price full hacking
Existing screed thickness to remove (avg) | 0.04 | m | Assumed 40 mm
New screed average thickness to falls | 0.05 | m | Assumed 50 mm avg (falls 1:80, min 30 mm at drain)
New screed volume | 147.9245 | m³
Cement for 1:3 screed (incl. 18% wastage) | 1570.9582 | bags | ~9 bags per m³
Sand for screed (incl. wastage) | 226.9162 | m³ | ~1.3 m³ per m³
BRC 610 mesh sheets (incl. laps & wastage) | 349 | sheets
Movement joints in screed | 595 | m | Bays ~5 x 5 m: approx. 1 m of joint per 5 m²
Up-turn length along walls / glass / raking columns (3rd-6th) | 930 | m | Inner ring perimeters ~643 m + 24 raking columns x 3.0 m x 4 floors ~288 m
Up-turn height | 0.3 | m | Item 4.5
Up-turn area (107 + 632 R + Reemat) | 279 | m²
Silicone joints along wall & glass at all balconies (item 6.0) | 1300 | m | Inner perimeters 3rd-6th ~643 m x 2 lines (floor/wall + glass)
3. RWDP / CORING COUNTS (from drawing symbols)
Floor | Coring points - main RWDP through slab / gutter wall | Coring points - new floor trap | Existing floor trap covers to replace | Remarks
1st Floor (RC gutter wall) | 48 | 0 | 0 | Yellow symbols on 2/11
3rd Floor | 49 | 49 | 0 | Red + blue symbols on 4/11
4th Floor | 49 | 48 | 0 | 5/11
5th Floor | 1 | 49 | 0 | 6/11
6th Floor | 0 | 0 | 12 | 7/11 - existing traps maintained, covers replaced
TOTAL | 147 | 146 | 12
Total new coring points (item 2.2) | 293 | points
Number of RWDP downpipes (level 5 to gutter) | 49 | no. | One per column bay
Pipe length per downpipe along raking column, L5 to L1 gutter | 24 | m | 18 m vertical x 1.35 slope factor
uPVC 110 mm pipe total (incl. branch connections & 10% wastage) | 1454.2 | m
uPVC pipe lengths (5.8 m) | 251 | lengths
Fittings (tees at traps, elbows, couplings) | 495 | no.
Pipe clips (every 1.5 m) | 970 | no.
Existing floor traps to decommission (end cap + concrete) - item 2.3 | 146 | no. | Assumed equal to new traps; verify on site
4. HOISTING (crane) - derived from the above
Materials to hoist up (t) | 464.4644 | t | Cement, sand, BRC, Sika products, pipes, plant allowance 5 t
Debris to lower (t) | 242.876 | t | Hacked screed at 2.0 t/m³ + gutter silt
Number of crane lifts | 863 | lifts | 0.85 t per lift + 30 misc. lifts
Crane days (incl. 2 contingency days) | 20 | days
Waste disposal trips | 55 | trips | 5 t per trip + general waste

## Rate Build-up
HOLY BUILDERS SDN. BHD.
RATE BUILD-UP - NET COST BY BQ ITEM (materials, labour, plant & logistics)
Every line is a formula linked to Quantities and Rates & Inputs. Type: M = material, L = labour, P = plant / logistics / preliminaries.
BQ item | Cost line | Quantity | Unit | Rate (RM) | Type | Amount (RM) | Basis
1.0 | PRELIMINARIES AND GENERALLY
1.0 | Site supervisor / foreman | 96 | day | 280 | L | 26880 | Full programme
1.0 | Site safety supervisor (working at height) | 96 | day | 260 | L | 24960 | Full programme
1.0 | Edge protection / mobile scaffold hire | 16 | week | 2200 | P | 35200
1.0 | Site office, store, toilet, water & electricity | 16 | week | 2400 | P | 38400
1.0 | Mixers, grinders, vacuum, small tools | 16 | week | 900 | P | 14400
1.0 | HSE: PPE, harnesses, signage, barricades, lifting plan | 1 | lump | 9500 | P | 9500
1.0 | Mobilisation / demobilisation, hoarding, daily cleaning | 1 | lump | 12000 | P | 12000 | Debris cleared daily; work outside office hours where directed
1.0 | Method statement, shop drawings, as-built, flood tests, Sika warranty | 1 | lump | 6500 | P | 6500
1.0 | Mobile crane 100 t - daily hire incl. operator | 20 | day | 5800 | P | 116000 | Hoisting of materials and lowering of debris (no lifts for waste permitted)
1.0 | Crane mobilisation / demobilisation | 6 | no. | 8000 | P | 48000
1.0 | Riggers / signalmen (2 nos.) | 40 | day | 150 | P | 6000
1.0 | Material delivery lorry trips | 47 | trip | 650 | P | 30550 | 10 t per trip
1.0 | Insurance (CAR, workmen) & bond charges - see Tender Summary | 0 | lump | 0 | P | 0 | Calculated on the Tender Summary as % of contract sum
2.1 | CORING WORK - IDENTIFYING CORING POINTS & TEST, PE REPORT
2.1 | Professional Engineer assessment & endorsed report | 1 | lump | 9000 | L | 9000
2.1 | Rebar scanning (GPR / cover meter) at each coring point | 293 | point | 15 | L | 4395
2.1 | Setting out of coring points (plumber + general worker) | 7.325 | day | 305 | L | 2234.125 | 40 points per day
2.2 | CORING 110 mm DIA. TO FLOOR SLAB / RC GUTTER WALL
2.2 | Coring crew (2 men) - labour | 41.8571 | man-day | 190 | L | 7952.8571
2.2 | Coring machine hire & diamond bit wear | 293 | point | 22 | P | 6446
2.2 | Making good around cores - repair mortar | 86.435 | bag | 125 | M | 10804.375 | 0.25 bag per point
2.3 | DECOMMISSIONING OF EXISTING RWDP
2.3 | Dewatering existing RWDP (pump hire & labour) | 4 | day | 410 | L | 1640 | Pump hire RM 180/day + 2 workers
2.3 | 4" PVC end caps | 153.3 | no. | 9 | M | 1379.7
2.3 | Concrete / grout to existing floor trap openings | 146 | no. | 18 | M | 2628
2.3 | Labour - cap and concrete existing traps | 7.3 | man-day | 190 | L | 1387 | 20 traps per man-day
2.4 | SUPPLY & INSTALL NEW 110 mm uPVC RWDP / FLOOR TRAP
2.4 | uPVC 110 mm Class D pipe (SIRIM) 5.8 m lengths | 251 | length | 68 | M | 17068 | Incl. 10% wastage in quantity
2.4 | Fittings - tees, elbows, couplings | 495 | no. | 28 | M | 13860
2.4 | Pipe clips / brackets c/w anchors | 970 | no. | 12 | M | 11640
2.4 | Floor traps c/w gratings (new) + replacement covers at 6th floor | 158 | no. | 85 | M | 13430
2.4 | Solvent cement, sealant at penetrations (Sikaflex) | 146.5 | no. | 26 | M | 3809 | Half cartridge per penetration
2.4 | Plumber labour - pipe installation on raking columns | 103.8714 | man-day | 190 | L | 19735.5714 | Incl. cutting access to glazing and connections to gutter
2.4 | General worker assisting (1 per plumber) | 103.8714 | man-day | 115 | L | 11945.2143
3.0 | DEMOLITION AND ASSOCIATED WORKS
3.0 | Removal of remaining debris, carting away & making good | 1 | lump | 4500 | P | 4500 | Allowance - loading, skips covered under 3.1
3.0 | General workers - demolition & making good | 12 | man-day | 115 | L | 1380
3.1 | HACKING EXISTING CEMENT SCREED & WATERPROOFING
3.1 | Hacking labour (breaker crews) | 422.6414 | man-day | 115 | L | 48603.7643 | Remaining portion only (see Quantities)
3.1 | Breaker / jack-hammer hire | 140.8805 | day | 95 | P | 13383.6452 | 1 breaker per 3 men, RM 95/day
3.1 | Debris chute / skip set-up per floor | 4 | floor | 1200 | P | 4800
3.1 | Disposal to contractor dumping ground | 55 | trip | 480 | P | 26400
4.1 | PREPARE SURFACE, PATCH / REPAIR CRACKS, RECTIFY PONDING, CLEAN
4.1 | Repair mortar for patching & local falls | 139.6407 | bag | 125 | M | 17455.091 | 1 bag per 25 m²
4.1 | Crack sealing - Sikaflex | 87.2755 | no. | 26 | M | 2269.1618
4.1 | Labour - grinding, patching, cleaning | 84.5283 | man-day | 190 | L | 16060.3743
4.1 | High-pressure water jet hire | 42.2641 | day | 180 | P | 7607.5457
4.1 | Water & consumables | 2958.49 | m² | 0.5 | M | 1479.245
4.2 | SUPPLY & APPLY 3 COATS SikaTop SEAL-107 (MY) ON ENTIRE RC SLAB (3rd-6th)
4.2 | SikaTop Seal-107 25 kg sets | 629 | set | 165 | M | 103785 | 1.5 kg/m²/coat x 3 coats + 18%
4.2 | Skilled applicators | 77.855 | man-day | 190 | L | 14792.45
4.2 | General worker - mixing / carrying (1 per 2 applicators) | 38.9275 | man-day | 115 | L | 4476.6625
4.2 | Curing (misting) & consumables | 2958.49 | m² | 0.5 | M | 1479.245
4.3 | CEMENT & SAND SCREED TO FALLS c/w SCUPPER DRAIN, BRC 610, MOVEMENT JOINTS (3rd-6th)
4.3 | Cement 50 kg bags | 1570.9582 | bag | 23 | M | 36132.0384
4.3 | Washed sand | 226.9162 | m³ | 75 | M | 17018.7137
4.3 | BRC 610 mesh | 349 | sheet | 95 | M | 33155
4.3 | Movement joints | 595 | m | 28 | M | 16660
4.3 | Screeders / masons | 268.9536 | man-day | 180 | L | 48411.6545 | Laid to falls, forming 300 x 50 mm scupper drain, steel trowel finish
4.3 | General workers - mixing & barrowing (1 per screeder) | 268.9536 | man-day | 115 | L | 30929.6682
4.3 | Mixer / barrows / curing | 2958.49 | m² | 1 | M | 2958.49
4.4 | SUPPLY & APPLY 3 LAYERS Sikalastic-632 R ON NEW SCREED & SCUPPER DRAIN (3rd-6th)
4.4 | Sikalastic U-Primer 14 kg pails | 50 | pail | 520 | M | 26000 | 0.20 kg/m² + 18%
4.4 | Sikalastic-632 R 21 kg pails | 350 | pail | 980 | M | 343000 | 0.70 kg/m²/layer x 3 + 18%
4.4 | Sika Reemat Premium - drain edges & outlets (300 mm strips) | 14 | roll | 480 | M | 6720 | Both edges of drain rings + outlets
4.4 | Sika Thinner C | 20 | tin | 65 | M | 1300
4.4 | Skilled applicators | 92.4528 | man-day | 190 | L | 17566.0344
4.4 | General worker (1 per 2 applicators) | 46.2264 | man-day | 115 | L | 5316.0367
4.5 | UP-TURNS ALONG WALL, GLASS & RAKING COLUMNS (items 4.2 & 4.4 systems)
4.5 | SikaTop Seal-107 25 kg sets - up-turns | 60 | set | 165 | M | 9900
4.5 | Sikalastic U-Primer + 632 R - up-turns (21 kg pails equiv.) | 37 | pail | 980 | M | 36260
4.5 | Sika Reemat Premium - full reinforcement of up-turns | 7 | roll | 480 | M | 3360
4.5 | Fittings, accessories & finishes to match existing colour | 930 | m | 6 | M | 5580 | Allowance RM 6/m
4.5 | Skilled applicators | 31 | man-day | 190 | L | 5890
5.0 | RC GUTTER - CLEAN, REPAIR & 3 LAYERS Sikalastic-632 R TO FLOOR AND WALL
5.0 | Water-jet cleaning & vegetation removal - labour | 42.2437 | man-day | 115 | L | 4858.029
5.0 | High-pressure water jet (150 bar) hire | 21.1219 | day | 180 | P | 3801.9357
5.0 | Disposal of silt / vegetation | 3 | trip | 480 | P | 1440
5.0 | Repair mortar - plastering to cracks & honeycomb | 65.7988 | bag | 125 | M | 8224.8543
5.0 | Sikalastic U-Primer 14 kg pails | 16 | pail | 520 | M | 8320
5.0 | Sikalastic-632 R 21 kg pails - floor & walls | 110 | pail | 980 | M | 107800
5.0 | Sika Reemat Premium - floor/wall angles & outlets | 5 | roll | 480 | M | 2400
5.0 | Skilled applicators - repair & coating | 33.1915 | man-day | 190 | L | 6306.3855
5.0 | General worker | 16.5958 | man-day | 115 | L | 1908.5114
6.0 | SILICONE SEAL - MAKE GOOD ALONG WALL & GLASS AT ALL BALCONIES
6.0 | Silicone sealant cartridges | 192 | no. | 22 | M | 4224 | 8 m per cartridge
6.0 | Backer rod, masking tape, cleaner | 1300 | m | 1.2 | M | 1560
6.0 | Skilled sealant applicator - removal & re-sealing | 37.1429 | man-day | 190 | L | 7057.1429
7.1 | PROVISIONAL - REMOVAL OF DEFECTIVE CEILING (per m²)
7.1 | Labour - removal, temporary dismantle of light fittings | 0.04 | man-day | 115 | L | 4.6 | Per m²
7.1 | Disposal | 1 | m² | 1.5 | P | 1.5 | Per m²
7.2 | PROVISIONAL - NEW PRIME FLEX 3 mm CEILING (per m²)
7.2 | Prime flex board, screws, jointing compound | 1 | m² | 16.52 | M | 16.52 | Per m²
7.2 | Labour - install, reinstate light fittings, plaster joints | 0.083333 | man-day | 190 | L | 15.8333 | Per m²
7.3 | PROVISIONAL - REPAIR CEILING WOODEN STRUCTURE (per m³)
7.3 | Treated timber | 1 | m³ | 3776 | M | 3776 | Per m³
7.3 | Carpenter labour | 6 | man-day | 190 | L | 1140 | Per m³
7.4 | PROVISIONAL - PAINTING INTERNAL CEILING, PRIMER + 2 COATS (per m²)
7.4 | Paint materials | 1 | m² | 5.31 | M | 5.31 | Per m²
7.4 | Painter labour | 0.025 | man-day | 190 | L | 4.75 | Per m²
7.5 | PROVISIONAL - ALUMINIUM FLASHING 1.0 mm c/w CAULKING (per m²)
7.5 | Aluminium flashing fabricated + caulking | 1 | m² | 112.1 | M | 112.1 | Per m²
7.5 | Labour | 0.25 | man-day | 190 | L | 47.5 | Per m²
7.6 | PROVISIONAL - GROUTING TO CRACKS (per point)
7.6 | Injection grout / epoxy per point | 1 | point | 32 | M | 32 | Per point
7.6 | Labour | 0.1 | man-day | 190 | L | 19 | Per point

## Item Pricing
HOLY BUILDERS SDN. BHD.
ITEM PRICING - NET COST, WARRANTY PROVISION, 28% MARGIN, TENDER PRICE
Net costs are summed from the Rate Build-up by BQ item. Warranty % applies to waterproofing items only. Tender price = (net + warranty) x (1 + margin).
BQ item | Description | Materials (RM) | Labour (RM) | Plant / logistics (RM) | Net cost (RM) | Warranty 2 yrs (RM) | Margin 28% (RM) | Tender price (RM) | Price basis
1.0 | Preliminaries and Generally | 0 | 51840 | 316550 | 368390 | 0 | 103149.2 | 471539.2 | Lump sum
2.1 | Coring - identify points, tests & PE report | 0 | 15629.125 | 0 | 15629.125 | 0 | 4376.155 | 20005.28 | Lump sum
2.2 | Coring 110 mm dia. to slab / RC gutter wall | 10804.375 | 7952.8571 | 6446 | 25203.2321 | 0 | 7056.905 | 32260.14 | Lump sum
2.3 | Decommissioning of existing RWDP | 4007.7 | 3027 | 0 | 7034.7 | 0 | 1969.716 | 9004.42 | Lump sum
2.4 | Supply & install new 110 mm uPVC RWDP / floor trap | 59807 | 31680.7857 | 0 | 91487.7857 | 0 | 25616.58 | 117104.37 | Lump sum
3.0 | Demolition and associated works | 0 | 1380 | 4500 | 5880 | 0 | 1646.4 | 7526.4 | Lump sum
3.1 | Hacking work to existing cement screed | 0 | 48603.7643 | 44583.6452 | 93187.4095 | 0 | 26092.4747 | 119279.88 | Lump sum
4.1 | Prepare surface, patch / repair, rectify ponding, clean | 21203.4978 | 16060.3743 | 7607.5457 | 44871.4178 | 1346.1425 | 12940.9169 | 59158.48 | Lump sum
4.2 | 3 coats SikaTop Seal-107 (MY) on entire RC slab | 105264.245 | 19269.1125 | 0 | 124533.3575 | 3736.0007 | 35915.4203 | 164184.78 | Lump sum
4.3 | Cement & sand screed to falls c/w scupper drain, BRC 610 | 105924.2421 | 79341.3227 | 0 | 185265.5648 | 5557.9669 | 53430.5889 | 244254.12 | Lump sum
4.4 | 3 layers Sikalastic-632 R on screed & scupper drain | 377020 | 22882.0711 | 0 | 399902.0711 | 11997.0621 | 115331.7573 | 527230.89 | Lump sum
4.5 | Up-turns along wall, glass & raking columns | 55100 | 5890 | 0 | 60990 | 1829.7 | 17589.516 | 80409.22 | Lump sum
5.0 | RC Gutter - clean, repair, 3 layers Sikalastic-632 R | 126744.8543 | 13072.9259 | 5241.9357 | 145059.716 | 4351.7915 | 41835.2221 | 191246.73 | Lump sum
6.0 | Silicone seal to wall & glass | 5784 | 7057.1429 | 0 | 12841.1429 | 385.2343 | 3703.3856 | 16929.76 | Lump sum
7.1 | Prov. - removal of defective ceiling (rate per m²) | 0 | 4.6 | 1.5 | 6.1 | 0 | 1.708 | 7.81 | Rate per unit (provisional)
7.2 | Prov. - new prime flex 3 mm ceiling (rate per m²) | 16.52 | 15.8333 | 0 | 32.3533 | 0 | 9.0589 | 41.41 | Rate per unit (provisional)
7.3 | Prov. - repair ceiling wooden structure (rate per m³) | 3776 | 1140 | 0 | 4916 | 0 | 1376.48 | 6292.48 | Rate per unit (provisional)
7.4 | Prov. - painting ceiling (rate per m²) | 5.31 | 4.75 | 0 | 10.06 | 0 | 2.8168 | 12.88 | Rate per unit (provisional)
7.5 | Prov. - aluminium flashing (rate per m²) | 112.1 | 47.5 | 0 | 159.6 | 0 | 44.688 | 204.29 | Rate per unit (provisional)
7.6 | Prov. - grouting to cracks (rate per point) | 32 | 19 | 0 | 51 | 0 | 14.28 | 65.28 | Rate per unit (provisional)
TOTAL (lump-sum items 1.0 - 6.0 only) |  | 871659.9143 | 323686.4815 | 384929.1267 | 1580275.5225 | 29203.8981 | 450654.2378 | 2060133.67
Notes:
1. Margin (28%) and the 2-year warranty provision are inputs on the Rates & Inputs sheet. Insurance & bond charges are added on the Tender Summary as a % of the contract sum.
2. Provisional items 7.1-7.6 are priced as unit rates (incl. margin) and multiplied by the BQ provisional quantities on the Tender Summary.
3. Item 3.1: the BQ states part of the hacking has been carried out - set the completed % on the Quantities sheet after the site visit.