## Crane Selection
CRANE SELECTION - HOISTING TO ROOF BALCONIES, WISMA BINTULU
Geometry from section drawing 8/11 (Ground-L1 = 6.0 m, L1-L6 = 4.5 m per floor; grid 9.0 m) and from the CAD plan take-off (balcony ring radii). Yellow = inputs; verify with the crane supplier load chart before hire.
1. CRANE STANDING POSITION & RIGGING INPUTS
Distance of crane slew centre from building centre (m) | 57 | Podium / 1st-floor gutter outer radius is 49.8 m; crane set up on ground outside the podium with outrigger half-spread + clearance ≈ 7 m
Landing point set in from balcony outer edge (m) | 1.5 | Load landed just inside the parapet / edge on the ring
Clearance above floor level for landing & parapet (m) | 1.5 | Parapet / upstand + landing clearance
Rigging height: cage + slings + hook block (m) | 3 | Pallet cage ~1.2 m + 4-leg sling ~1.5 m + hook block
Safety clearance under boom tip (m) | 1
Design load per lift incl. cage / pallet (t) | 1 | ~36 pails of Sikalastic-632 R (0.76 t) or 32 bags of screed (0.8 t) in a 0.1 t cage, max 1.0 t
Dynamic / safety factor on load | 1.25 | Rated capacity required = design load x factor (crane chart utilisation ≤ 80%)
2. REQUIRED REACH PER LEVEL
Level | Floor level above ground (m) | Balcony / gutter outer radius from building centre (m) | Element | Required hook height (m) | Required working radius (m) | Rated capacity required at that radius (t) | Remarks
Level 1 | 6 | 49.8 | Existing RC gutter (podium roof edge) | 11.5 | 8.7 | 1.25 | Gutter at podium perimeter; short radius, light loads
Level 3 | 15 | 38.52 | Balcony floor + scupper drain | 20.5 | 19.98 | 1.25
Level 4 | 19.5 | 32.75 | Balcony floor + scupper drain | 25 | 25.75 | 1.25
Level 5 | 24 | 26.35 | Balcony floor + scupper drain | 29.5 | 32.15 | 1.25
Level 6 | 28.5 | 20.4 | Balcony floor + scupper drain | 34 | 38.1 | 1.25 | Governs crane size: highest and furthest-in balcony
GOVERNING (max) |  |  |  | 34 | 38.1 | 1.25
3. CRANE OPTIONS (indicative load-chart data - confirm with supplier chart for the actual boom configuration)
Crane class | Type | Main boom (m) | Max. working radius at 1.0 t with hook ≥ 33 m (m, indicative) | Capacity at governing radius (t, indicative) | Reach OK? | Capacity OK? | Verdict / remarks
50 t | All-terrain / truck mobile crane | 40 | 27 | 0.9 | NO | NO | Too short: boom tip cannot reach Level 6 balcony at the required radius
80 t | All-terrain mobile crane | 50 | 34 | 1.1 | NO | NO | Marginal: reaches Level 5; Level 6 only if crane can stand closer (≤ 52 m from centre)
100 t | All-terrain mobile crane | 60 | 42 | 2.3 | YES | YES | RECOMMENDED - reaches all levels incl. Level 6 with 1.0 t loads at ≤ 80% utilisation
130 t | All-terrain mobile crane | 60 | 46 | 3.2 | YES | YES | Suitable, extra margin for 1.5 t loads / standing further out; higher rate
250 t | All-terrain mobile crane | 72 | 55 | 4 | YES | YES | Over-capacity; only if crane must stand on the service road (~69 m from centre)
RECOMMENDATION
Hire a 100 t class all-terrain mobile crane with ~60 m main boom (e.g. Liebherr LTM 1100 / Tadano ATF 100 / Sany STC1000 class). Governing lift: ~1.0 t to Level 6 balcony at ~38 m radius and ~34 m hook height. Set up on firm ground outside the podium (outrigger mats on compacted ground; check the service road / drains for outrigger loads up to ~45 t per pad).
The balconies are rings, so each floor is served from 2-3 crane standing positions around the building (crane repositions ~1 hr each) and materials are trolleyed around the ring. Daily callout hire is more economical than monthly hire because hoisting is needed only for about 1 week in total, spread over the programme (see Hoisting Programme).
Alternative for the Level 1 gutter only: a 50 t crane or a telehandler / material hoist, since the gutter is at the podium edge (6 m high, ~8.7 m radius).
All lifts under a lifting plan by a competent person; crane with valid DOSH PMA certificate; operator licensed; signalman / rigger; tag lines; exclusion zone below the lifting path; no lifting in wind > 9 m/s or lightning.

## Hoisting Programme
HOISTING PROGRAMME - MATERIALS TO BE LIFTED AND CRANE DAYS REQUIRED
Material quantities include 18% wastage (from the Material Requirement schedule). Screed and debris are allowances - adjust the yellow cells.
1. HOISTING INPUTS
Payload per lift, net of cage (t) | 0.85 | Cage / pallet 1.0 t gross less 0.15 t cage & pallet
Lifts per hour (cycle incl. hook-up, lift ~35 m, land, unhook, return) | 7 | ~8.5 min cycle at Level 6; faster at lower levels
Productive crane hours per day | 7 | 8 h shift less set-up, breaks, repositioning
Crane repositions per floor (no.) | 2 | Ring served from 2-3 standing positions
Time per reposition (h) | 1 | Outriggers in, travel, set up, re-level
Screed to falls - average thickness (m) | 0.03 | Set to 0 if no screed; 30 mm average over balcony floors
Screed density, bagged dry material (t/m³) | 2 | Pre-bagged sand-cement screed, 25-40 kg bags
Debris / waste to be lowered (t per m²) | 0.005 | Old coating, loose screed, silt from gutter ~5 kg/m²
Tools, plant & miscellaneous lifts per floor (no.) | 6 | Mixers, grinders, water drums, barriers, rubbish skips
2. MATERIALS TO HOIST PER FLOOR (tonnes)
Floor | Floor area (m²) | Gutter / drain area (m²) | SikaTop Seal-107 (t) | Sikalastic U-Primer (t) | Sikalastic-632 R (t) | Repair mortar & ancillaries (t) | Screed to falls (t) | Debris down (t) | Total up-lifts (t) | No. of lifts (incl. debris & misc.) | Crane hours | Crane days
Level 1 gutter | 0 | 309.84 | 1.6453 | 0 | 0 | 0.118 | 0 | 1.5492 | 1.7632 | 11 | 3.5714 | 0.5102
Level 3 | 960.85 | 110.49 | 0.5867 | 0.22676 | 2.381 | 0.236 | 57.651 | 5.3567 | 61.0814 | 85 | 14.1429 | 2.0204
Level 4 | 793.02 | 96.79 | 0.51395 | 0.18715 | 1.9651 | 0.195 | 47.5812 | 4.449 | 50.4424 | 72 | 12.2857 | 1.7551
Level 5 | 553.47 | 72.02 | 0.38243 | 0.13062 | 1.3715 | 0.136 | 33.2082 | 3.1275 | 35.2287 | 52 | 9.4286 | 1.3469
Level 6 | 380.76 | 58.6 | 0.31117 | 0.08986 | 0.94352 | 0.094 | 22.8456 | 2.1968 | 24.2842 | 38 | 7.4286 | 1.0612
TOTAL | 2688.1 | 647.74 | 3.4395 | 0.63439 | 6.6611 | 0.779 | 161.286 | 16.6792 | 172.8 | 258 | 46.8571 | 6.6939
Crane days required (rounded up to whole days) | [11 empty] | 7
Add: contingency days (weather, waiting, re-lifts) | [11 empty] | 2
TOTAL CRANE DAYS TO ALLOW | [11 empty] | 9
Notes:
1. Hoisting is phased floor by floor to suit the works programme (Level 6 first, then 5, 4, 3, gutter), so the crane is called out for 1-2 days per floor rather than kept on site continuously.
2. Screed quantity is an allowance (average 30 mm). If screeding to falls is not in the contract scope, set the thickness to 0 - crane days then fall to roughly 2 days plus contingency.
3. Lifts per hour assume a pallet cage with pre-loaded pallets at ground level and a rigger at each landing point; two landing points per floor.

## Logistics Cost
LOGISTICS & CRANE HIRE COST SUMMARY (RM)
Indicative Sarawak / Bintulu hire rates for budgeting only - obtain quotations from local crane hirers. Yellow = inputs.
1. CRANE HIRE RATES (indicative, operator included, 8-hour day, excl. SST)
Crane class | Daily rate (RM/day) | Monthly rate (RM/month, 26 days) | Mobilisation + demobilisation (RM, lump sum) | Rigger / signalman (RM/day) | Remarks
50 t | 2800 | 48000 | 4000 | 150 | Suitable for Level 1 gutter only
80 t | 4200 | 70000 | 6000 | 150 | Marginal reach for Level 6
100 t | 5800 | 92000 | 8000 | 150 | RECOMMENDED
130 t | 7500 | 118000 | 10000 | 150 | Extra margin
250 t | 13000 | 200000 | 20000 | 200 | Only if standing on service road
2. SELECTED CRANE & HIRE BASIS
Selected crane class | 100 t | Type exactly as in the rate table (50 t / 80 t / 100 t / 130 t / 250 t)
Crane days required (from Hoisting Programme, incl. contingency) | 9
Number of separate call-outs (mobilisations) for daily hire | 5 | One call-out per floor (L6, L5, L4, L3, gutter) - reduce if floors are combined
Months on hire if monthly basis | 1
Daily rate of selected crane | 5800
Monthly rate of selected crane | 92000
Mob/demob of selected crane (per call-out) | 8000
Rigger / signalman rate | 150
3. CRANE COST - DAILY HIRE vs MONTHLY HIRE
Cost item | Option A: Daily call-out hire (RM) | Option B: Monthly hire (RM) | Basis
Crane hire | 52200 | 92000 | A: days x daily rate; B: months x monthly rate
Mobilisation / demobilisation | 40000 | 8000 | A: per call-out; B: once
Rigger / signalman (2 nos.) | 2700 | 7800 | Two riggers (ground + landing)
Outrigger mats / ground protection & lifting plan | 2500 | 2500 | Allowance (steel plates / timber mats hire, competent-person lifting plan)
Pallet cage / lifting gear hire & inspection | 1500 | 1500 | Allowance
Road / site permit, traffic control, barricades | 1500 | 1500 | Allowance - BDA / building management
SUB-TOTAL CRANE & LIFTING | 100400 | 113300
Cheaper option | Option A - daily hire | 12900 | Saving vs the other option
4. MATERIAL TRANSPORT & OTHER LOGISTICS
Item | Quantity | Unit rate (RM) | Cost (RM) | Basis
Supplier delivery - Sika materials to site (lorry trips, 10 t) | 2 | 1800 | 3600 | ~12 t Sika products from Sika Kimia / stockist (Kuching / Bintulu) - confirm freight terms
Supplier delivery - screed & repair mortar (lorry trips, 10 t) | 17 | 600 | 10200 | ~165 t bagged screed + mortar, local supplier
Forklift / pallet jack hire for ground handling (days) | 10 | 350 | 3500 | Loading cages at ground level
Trolleys / barrows for distribution around balcony rings (nos.) | 6 | 250 | 1500 | Purchase
Waste removal skips (nos.) | 6 | 450 | 2700 | Debris, empty pails - licensed disposal
Site store container hire (months) | 3 | 900 | 2700 | Shaded, locked store for solvent-based products
SUB-TOTAL TRANSPORT & LOGISTICS |  |  | 24200
5. LOGISTICS COST SUMMARY
Item | Option A: Daily hire (RM) | Option B: Monthly hire (RM)
Crane & lifting | 100400 | 113300
Transport & other logistics | 24200 | 24200
TOTAL LOGISTICS COST (excl. SST) | 124600 | 137500
Logistics cost per m² of waterproofing (RM/m², Option A) | 37.3519 | Total treated area 3,335.84 m²
Notes:
1. Crane rates are indicative budget figures for Sarawak (2025/26) and vary with availability, distance from the crane yard (Bintulu / Miri / Sibu) and hire duration - obtain at least two quotations.
2. Daily hire is normally the cheaper option here because only ~1-2 crane days per floor are needed; monthly hire is only worth considering if the crane is also used for other trades.
3. SST, overtime beyond 8 hours, standby days due to weather and night work are excluded - add as applicable.
4. Change the selected crane class in Section 2 and all costs update; change days / contingency on the 'Hoisting Programme' sheet.